## INTRO
Annual Work Plan
As part of the global efforts to accelerate expansion of preventive chemotherapy (PC) for elimination and control of lymphatic filariasis, schistosomiasis, soil-transmitted helminthiases and onchocerciasis, the World Health Organization (WHO) facilitates the supply of necessary medicines. In order to request for medicines, submission of the Annual Work Plan together with the Joint Request for selected PC medicines and the Joint Reporting Form is a requisite.
Annual Work Plan allows the national programmes to identify the specific objectives to be achieved in the year, to focus on the key activities that needs to be implemented to achieve the said objectives, and to identify the gap in financial and technical resources to achieve the objectives. It also allows WHO to closely monitor the progress of the national programmes, and to identify the obstacles and coordinate for provision of financial and technical support in time.
Information to be included in the Annual Work Plan
Name of country
Implementation year
Relevant preventive chemotherapy diseases
Specific programmatic targets to achieve in the year
Annual work plan matrix comprising a list of activities and sub-activities with:
- Timeline of implementation
- Estimated cost
- Available or committed funds
- Funding gap
- Funders
Format of the Annual Work Plan
i) | There is no prescribed format; the annual work plan can be excel or word file as long as the required information is contained. Example is given in the following worksheet.
ii) | Annual work plan matrix can be automatically generated using the Tool for Integrated Planning and Costing (TIPAC).

## ANNUAL_WORKPLAN
ANNUAL WORK PLAN
1. Name of country | Liberia
2. Implementation year | Apr | 2018 | to | Mar | 2019
| month | year |  | month | year
3. Relevant PC diseases
4. Specific goals to be achieved in the year | i) To achieved 84%Therapeutic coverage for 2018
ii) Conduct Epidemiological and Entomological evaluation for Southeast and Southwest Project
iii) To conduct Pre TAS for LF
5. Annual work plan matrix
Activities and sub-activities | Timeline for implementation | [11 empty] | Estimated cost | Available funding | Funding gap | Funders
| Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | USD | USD | USD
Annual planning and review | [14 empty] | 0
Annual planning meeting | [14 empty] | 0 | bar: Timeline for implementation Dec
National stakeholders meeting | [14 empty] | 0 | bar: Timeline for implementation Jun; Timeline for implementation Sep
Training | [14 empty] | 0
Training of drug distributors | [14 empty] | 0 | bar: Timeline for implementation May
National TAS training | [14 empty] | 0 | bar: Timeline for implementation Aug
Social mobilization | [14 empty] | 0
Drug logistics | [14 empty] | 0
Drug request | [14 empty] | 0 | bar: Timeline for implementation Apr
Drug repackaging | [14 empty] | 0 | bar: Timeline for implementation Apr
Drug transportation to districts | [14 empty] | 0 | bar: Timeline for implementation Apr
Drug distribution | [14 empty] | 0
MDA1 (IVM + ALB) | [14 empty] | 0 | bar: Timeline for implementation May to Timeline for implementation Jun
MDA2 (DEC + ALB) | [14 empty] | 0
MDA3 (IVM) | [14 empty] | 0 | bar: Timeline for implementation Jun to Timeline for implementation Jul
T1 (ALB/MBD + PZQ) | [14 empty] | 0
T2 (PZQ) | [14 empty] | 0 | bar: Timeline for implementation Jun to Timeline for implementation Jul
T3 (ALB/MBD) | [14 empty] | 0
Monitoring and evaluation | [14 empty] | 0 | bar: Timeline for implementation May
LF sentinel/spot check sites survey | [14 empty] | 0
SCH and/or STH prevalence survey | [14 empty] | 0 | bar: Timeline for implementation May
ONC epidemiological survey | [14 empty] | 0 | bar: Timeline for implementation Jul
LF TAS | [14 empty] | 0 | bar: Timeline for implementation Sep
Evaluation Unit 1 | [14 empty] | 0
Evaluation Unit 2 | [14 empty] | 0
6. Attachment
LF
STH
SCH
ONCHO
Joint Request for Selected PC Medicines
Joint Reporting Form

## Example
ANNUAL WORK PLAN
1. Name of country | Murkonia
2. Implementation year | May | 2013 | to | Apr | 2014
| month | year |  | month | year
3. Relevant PC diseases
4. Specific goals to be achieved in the year | i) To achieve 75% national coverage for STH and SCH
ii) To conduct LF TAS in 2 Evaluation Units
iii) To conduct epidemiological survey for all PC diseases
5. Annual work plan matrix
Activities and sub-activities | Timeline for implementation | [11 empty] | Estimated cost | Available funding | Funding gap | Funders
| May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | USD | USD | USD
Annual planning and review | [12 empty] | 10600 | 6360 | 4240 | Government funding | bar: Timeline for implementation May to Timeline for implementation Jun
Annual planning meeting | [12 empty] | 5300 | 3180 | 2120 | Government funding | bar: Timeline for implementation May
National stakeholders meeting | [12 empty] | 5300 | 3180 | 2120 | Government funding | bar: Timeline for implementation Jun
Training | [12 empty] | 14000 | 0 | 14000 | bar: Timeline for implementation Sep; Timeline for implementation Jan
Training of drug distributors | [12 empty] | 7000 | 0 | 7000 | bar: Timeline for implementation Sep
National TAS training | [12 empty] | 7000 | 0 | 7000 | bar: Timeline for implementation Jan
Social mobilization | [12 empty] | 7000 | 0 | 7000 | bar: Timeline for implementation Oct
Drug logistics | [12 empty] | 63678 | 0 | 63678 | bar: Timeline for implementation Sep; Timeline for implementation Mar
Drug request | [12 empty] | 54483.55 | 0 | 54483.55 | bar: Timeline for implementation Mar
Drug repackaging | [12 empty] | 1766.6 | 0 | 1766.6 | bar: Timeline for implementation Sep
Drug transportation to districts | [12 empty] | 7427.75 | 0 | 7427.75 | bar: Timeline for implementation Sep
Drug distribution | [12 empty] | 326901 | 0 | 326901 | bar: Timeline for implementation Nov to Timeline for implementation Dec
MDA1 (IVM + ALB) | [12 empty] | 54483.55 | 0 | 54483.55 | bar: Timeline for implementation Nov to Timeline for implementation Dec
MDA2 (DEC + ALB) | [12 empty] | 54483.55 | 0 | 54483.55 | bar: Timeline for implementation Nov to Timeline for implementation Dec
MDA3 (IVM) | [12 empty] | 54483.55 | 0 | 54483.55 | bar: Timeline for implementation Nov to Timeline for implementation Dec
T1 (ALB/MBD + PZQ) | [12 empty] | 54483.55 | 0 | 54483.55 | bar: Timeline for implementation Dec
T2 (PZQ) | [12 empty] | 54483.55 | 0 | 54483.55 | bar: Timeline for implementation Dec
T3 (ALB/MBD) | [12 empty] | 54483.55 | 0 | 54483.55 | bar: Timeline for implementation Dec
Monitoring and evaluation | [12 empty] | 29400 | 14700 | 14700 | Funder 1, Funder 2 | bar: Timeline for implementation Feb; Timeline for implementation Apr
LF sentinel/spot check sites survey | [12 empty] | 13500 | 13500 | 0 | Funder 1 | bar: Timeline for implementation Feb
SCH and/or STH prevalence survey | [12 empty] | 1200 | 1200 | 0 | Funder 2 | bar: Timeline for implementation Feb
ONC epidemiological survey | [14 empty] | 0 | bar: Timeline for implementation Feb
LF TAS | [12 empty] | 13500 | 13500 | 0 | Funder 1 | bar: Timeline for implementation Apr
Evaluation Unit 1 | [12 empty] | 600 | 600 | 0 | Funder 2 | bar: Timeline for implementation Apr
Evaluation Unit 2 | [12 empty] | 600 | 600 | 0 | Funder 2 | bar: Timeline for implementation Apr
6. Attachment
Joint Request for Selected PC Medicines
Joint Reporting Form
LF
STH
SCH
ONCHO