## INTRO
Annual Work Plan
As part of the global efforts to accelerate expansion of preventive chemotherapy (PC) for elimination and control of lymphatic filariasis, schistosomiasis, soil-transmitted helminthiases and onchocerciasis, the World Health Organization (WHO) facilitates the supply of necessary medicines. In order to request for medicines, submission of the Annual Work Plan together with the Joint Request for selected PC medicines and the Joint Reporting Form is a requisite.
Annual Work Plan allows the national programmes to identify the specific objectives to be achieved in the year, to focus on the key activities that needs to be implemented to achieve the said objectives, and to identify the gap in financial and technical resources to achieve the objectives. It also allows WHO to closely monitor the progress of the national programmes, and to identify the obstacles and coordinate for provision of financial and technical support in time.
Information to be included in the Annual Work Plan
Name of country
Implementation year
Relevant preventive chemotherapy diseases
Specific programmatic targets to achieve in the year
Annual work plan matrix comprising a list of activities and sub-activities with:
- Timeline of implementation
- Estimated cost
- Available or committed funds
- Funding gap
- Funders
Format of the Annual Work Plan
i) | There is no prescribed format; the annual work plan can be excel or word file as long as the required information is contained. Example is given in the following worksheet.
ii) | Annual work plan matrix can be automatically generated using the Tool for Integrated Planning and Costing (TIPAC).

## ANNUAL_WORKPLAN
ANNUAL WORK PLAN
1. Name of country |  |  |  | SIERRA LEONE
2. Implementation year |  |  |  | Jan | 2018 | to | Dec | 2018
|  |  |  | month | year |  | month | year
3. Relevant PC diseases
4. Specific goals to be achieved in the year |  |  |  | i) Strengthen the capacity of the NTD Programme to conduct surveillance, monitoring and supervision and evaluation of all NTD activities and ensure feedback at all levels.
ii) Strengthen capacity of NTDCP and Districts staff on NTD implementation activities,
iii) Mobidity Managent for LF
5. Annual work plan matrix 2017/2018
| 2017 |  |  | 2018
Activities and sub-activities | [15 empty] | Estimated cost | Available funding | Funding gap | Funders
| Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | USD | USD | USD
Annual Review Meeting and Assessment
Annual Review Meeting for NTDs | [15 empty] | 12367 | 12367 | 0 | USAID/HKI | bar: Nov
Transmission Assessment Survey LF in 1 IU | [15 empty] | 12500 | 12500 | 0 | USAID/HKI | bar: Mar
MDA-Western Area Activities
Advocacy meeting with Stake holders | [15 empty] | 4774 | 4774 | 0 | USAID/HKI | bar: Feb
Advocacy meeting with Private Practitioners | [15 empty] | 2276 | 2276 | 0 | USAID/HKI | bar: Feb
Social Mobilisation | [15 empty] | 38985 | 38985 | 0 | USAID/HKI | bar: Feb
Training of PHU Staff | [15 empty] | 4799 | 4799 | 0 | USAID/HKI | bar: Mar
Training of Community Health Workers | [15 empty] | 22007 | 22007 | 0 | USAID/HKI | bar: Apr
MDA-LF-Western Area | [15 empty] | 68920 | 68920 | 0 | USAID/HKI | bar: Apr
MDA-SCH 7 Districts Activities | [17 empty] | 0
Advocacy Meetings | [15 empty] | 15353 | 15353 | 0 | USAID/HKI | bar: Dec
Training of Supervisors | [15 empty] | 9521 | 9521 | 0 | USAID/HKI | bar: Dec
Training & Refresher Training of PHU Staff | [15 empty] | 26245 | 26245 |  | USAID/HKI | bar: Dec
Social Mobilization | [15 empty] | 40200 | 40200 | 0 | USAID/HKI | bar: Jan
Distribution of Logistics and Drugs | [15 empty] | 4849 | 4849 | 0 | USAID/HKI | bar: Jan
Feeding of School Children Prior to PZQ | [15 empty] | 62608 | 62608 |  | USAID/HKI | bar: Feb
MDA SCH | [15 empty] | 80985 | 80985 | 0 | USAID/HKI | bar: Feb
Collection, Analysis and Reporting | [15 empty] | 4580 | 4580 | 0 | USAID/HKI & SIGHTSAVERS | bar: Feb
MDA ONE Oncho-LF&STH 12 HDs Activities | [17 empty] | 0 | bar: Oct to Dec
Training of Trainers | [15 empty] | 9111 | 9111 | 0 | USAID/HKI | bar: Jan
Advocacy Meetings | [15 empty] | 14438 | 14438 | 0 | USAID/HKI | bar: Jan
Training and Refresher Training of PHU Staff | [15 empty] | 61585 | 61585 | 0 | USAID/HKI | bar: Jan
Cross Border Meeting | [15 empty] | 15326 | 15326 | 0 | USAID/HKI | bar: Feb
Social Mobilization | [15 empty] | 55944 | 55944 | 0 | USAID/HKI | bar: Feb
Training and Refresher Training of CDDs | [15 empty] | 145288 | 145288 | 0 | USAID/HKI | bar: Mar
Distribution of Logistics and Drugs | [15 empty] | 7510 | 7510 | 0 | USAID/HKI | bar: Mar
MDA-Oncho-LF | [15 empty] | 202923 | 202923 | 0 | USAID/HKI | bar: Apr
Collection, Analysis and Reporting-Oncho-LF | [15 empty] | 25100 | 25100 | 0 | bar: May
Second round ONCHO MDA Activities 12 HDs | [17 empty] | 0 | bar: Oct to Dec
Training of Trainers | [15 empty] | 9240.7865 | 9240.7865 | 0 | SIGHTSAVERS
Advocacy Meetings | [15 empty] | 14341.3955 | 14341.3955 | 0 | SIGHTSAVERS | bar: Aug
Training and Refresher Training of PHU Staff | [15 empty] | 57814.5119 | 57814.5119 | 0 | SIGHTSAVERS | bar: Sep
Social Mobilization | [15 empty] | 57630.0679 | 57630.0679 | 0 | SIGHTSAVERS | bar: Oct
Training and Refresher Training of CDDs | [15 empty] | 139808.827 | 139808.827 | 0 | SIGHTSAVERS | bar: Oct
Distribution of Logistics and Drugs | [15 empty] | 9366.9741 | 9366.9741 | 0 | SIGHTSAVERS | bar: Oct
MDA-Oncho | [15 empty] | 170081.7818 | 170081.7818 | 0 | SIGHTSAVERS | bar: Nov
Collection, Analysis and Reporting | [15 empty] | 24642.4221 | 24642.4221 | 0 | bar: Dec
Special Advocacy Meeting | [17 empty] | 0 | bar: Oct to Dec
NTD Curriculum Development Workshop | [15 empty] | 14148 | 14148 | 0 | USAID/HKI | bar: May
NTD Expert Committee Meeting | [15 empty] | 10000 | 10000 | 0 | SIGHTSAVERS | bar: Jun; Nov
NTD mano River Union Meeting | [15 empty] | 15981.5556 | 15981.5556 | 0 | USAID/HKI/SIGHTSAVERS | bar: Oct
Capacity Building on M&E | [15 empty] | 30000 | 0 | 30000 | WHO | bar: Sep
Adminstrative Running Cost and General | [15 empty] | 22098 | 6000 | 16098 | USAID/HKI
Vehicle Maintinance and Repairs | [15 empty] | 25000 | 8000 | 17000 | USAID/HKI | bar: Apr
Procument of 5 new Land Cruiser vehicles for supportive supervision, coordination and distribution of logistics | [15 empty] | 300000 | 0 | 300000 | AFRO/WHO/ESPEN | bar: Apr
Monitoring and evaluation | [17 empty] | 0 | bar: Oct to Dec
GWD Surveillance in 14 Districts | [15 empty] | 23098 | 0 | 23098 | WHO | bar: Nov to Dec
NTD Morbidity Assessment Survey in 14 Districts | [15 empty] | 56932 | 0 | 56932 | HKI
NTD Morbidity Management in 14 Districts | [15 empty] | 300000 | 0 | 300000 | WHO/MOHS | bar: Aug
Buruli Ulcer Assessment Survey | [15 empty] | 660000 | 0 | 660000 | WHO | bar: Aug to Sep
Human African Trypanosomiasis Assessment Survey | [15 empty] | 200000 | 0 | 200000 | WHO
6. Attachment
LF
STH
SCH
ONCHO
Joint Request for Selected PC Medicines
Joint Reporting Form

## Example
ANNUAL WORK PLAN
1. Name of country | Murkonia
2. Implementation year | May | 2013 | to | Apr | 2014
| month | year |  | month | year
3. Relevant PC diseases
4. Specific goals to be achieved in the year | i) To achieve 75% national coverage for STH and SCH
ii) To conduct LF TAS in 2 Evaluation Units
iii) To conduct epidemiological survey for all PC diseases
5. Annual work plan matrix
Activities and sub-activities | Timeline for implementation | [11 empty] | Estimated cost | Available funding | Funding gap | Funders
| May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | USD | USD | USD
Annual planning and review | [12 empty] | 10600 | 6360 | 4240 | Government funding | bar: Timeline for implementation May to Timeline for implementation Jun
Annual planning meeting | [12 empty] | 5300 | 3180 | 2120 | Government funding | bar: Timeline for implementation May
National stakeholders meeting | [12 empty] | 5300 | 3180 | 2120 | Government funding | bar: Timeline for implementation Jun
Training | [12 empty] | 14000 | 0 | 14000 | bar: Timeline for implementation Sep; Timeline for implementation Jan
Training of drug distributors | [12 empty] | 7000 | 0 | 7000 | bar: Timeline for implementation Sep
National TAS training | [12 empty] | 7000 | 0 | 7000 | bar: Timeline for implementation Jan
Social mobilization | [12 empty] | 7000 | 0 | 7000 | bar: Timeline for implementation Oct
Drug logistics | [12 empty] | 63678 | 0 | 63678 | bar: Timeline for implementation Sep; Timeline for implementation Mar
Drug request | [12 empty] | 54483.55 | 0 | 54483.55 | bar: Timeline for implementation Mar
Drug repackaging | [12 empty] | 1766.6 | 0 | 1766.6 | bar: Timeline for implementation Sep
Drug transportation to districts | [12 empty] | 7427.75 | 0 | 7427.75 | bar: Timeline for implementation Sep
Drug distribution | [12 empty] | 326901 | 0 | 326901 | bar: Timeline for implementation Nov to Timeline for implementation Dec
MDA1 (IVM + ALB) | [12 empty] | 54483.55 | 0 | 54483.55 | bar: Timeline for implementation Nov to Timeline for implementation Dec
MDA2 (DEC + ALB) | [12 empty] | 54483.55 | 0 | 54483.55 | bar: Timeline for implementation Nov to Timeline for implementation Dec
MDA3 (IVM) | [12 empty] | 54483.55 | 0 | 54483.55 | bar: Timeline for implementation Nov to Timeline for implementation Dec
T1 (ALB/MBD + PZQ) | [12 empty] | 54483.55 | 0 | 54483.55 | bar: Timeline for implementation Dec
T2 (PZQ) | [12 empty] | 54483.55 | 0 | 54483.55 | bar: Timeline for implementation Dec
T3 (ALB/MBD) | [12 empty] | 54483.55 | 0 | 54483.55 | bar: Timeline for implementation Dec
Monitoring and evaluation | [12 empty] | 29400 | 14700 | 14700 | Funder 1, Funder 2 | bar: Timeline for implementation Feb; Timeline for implementation Apr
LF sentinel/spot check sites survey | [12 empty] | 13500 | 13500 | 0 | Funder 1 | bar: Timeline for implementation Feb
SCH and/or STH prevalence survey | [12 empty] | 1200 | 1200 | 0 | Funder 2 | bar: Timeline for implementation Feb
ONC epidemiological survey | [14 empty] | 0 | bar: Timeline for implementation Feb
LF TAS | [12 empty] | 13500 | 13500 | 0 | Funder 1 | bar: Timeline for implementation Apr
Evaluation Unit 1 | [12 empty] | 600 | 600 | 0 | Funder 2 | bar: Timeline for implementation Apr
Evaluation Unit 2 | [12 empty] | 600 | 600 | 0 | Funder 2 | bar: Timeline for implementation Apr
6. Attachment
Joint Request for Selected PC Medicines
Joint Reporting Form
LF
STH
SCH
ONCHO