## Work Plan 2018
Annual work plan matrix and timeline - FY 2018
|  | Budget items | Timeline for implementation
Activities - Sub-activities - Districts | Description |  | 2017-07-17 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01
SP1: NTD Coordination
Office Management
Procure office stationaries |  | inktonner, papers, desks, tables,
Office communiction |  | mailing/courier service charges, Internet fees, website fees, telephone bills, office service and repairs /mainteinance
software |  | software
office maintainance and entertainment |  | tea, coffee, sugar, milk, water
Program Vehicles
Procurement of vehicles
Maintenance of vehicles
Supporting staff salaries
Office Management and Furniture
coordiation meetings |  | conference packages
SP1: Strengthen Government Ownership, Advocacy, Coordination and Partnership
National advocacy meeting
NTD Advocacy and awareness and Fundrising dinner | Identified region by interesting donor. Currently Arusha, e.g. END fund Dinners | bar: 2018-06-01
Fundraising with local companies ---PPP --for ntd fundraising and sustainability | eg.develop biz plan, reach out to local companies
NTD Learning day | eg.develop biz plan, reach out to local companies | venue, transport, entertainment, perdiems, stationaries, communication, | bar: 2018-06-01
Highlevel sensitisation meeting | with MDA strategy, scale down, new leadership, e.t.c, | venue, transport, perdiems, stationaries, communication | bar: 2017-09-01; 2017-12-01; 2018-03-01; 2018-06-01; 2018-09-01; 2018-12-01
Press conference and press release | Pre MDA in key areas, e.g. big cities, special populations, | stationary, venue, allowances,
Regional Advocacy meeting
Advocay meeting with regional authorities | all regions, to be done as part of their planned activities (routines) but include NTD agenda | no cost to NTDCP (only TA)
Districts Advocacy Meeting
Advocay meeting for selected district with district authorities | all districts, to be done as part of their planned activities (routines) but include NTD agenda | no cost to NTDCP (only TA)
Advocay meeting for selected district with district authorities | in targeted district with issues, e.g. Suboptimal MDA uptake, persistent low coverage, presistent diseases, scalling up of morbidity interventions, e.t.c | conference package, allowances, stationaries, transport,
Advocay meeting for selected district with district authorities | in targeted districts with issues, e.g. Suboptimal MDA uptake, e.t.c: Kigoma region- uvinza, e.t.c, | conference package, allowances, stationaries, transport,
Advocay meeting for selected district with district authorities | In targeted districts with issues, e.g. persistent low coverage/presistent diseases: Manyoni, Itigi, Kalambo, chamwino, Simanjiro, Kiteto, Longido, Monduli, | conference package, allowances, stationaries, transport,
Advocay meeting for selected district WASH partners for trachoma elimination | In targeted districts with WASH issues, e.g. Dodoma, Manyara, Singida, Arusha, | conference package, allowances, stationaries, transport,
Advocay meeting for selected districts with Integrated Vector Management IVM partners for LF and Oncho elimination | In targeted districts with vectors contorl issues: Urban areas for Mosquito control, and also Ruvuma, Tanga, | conference package, allowances, stationaries, transport,
Advocay meeting for selected district WASH and malacology partners for SCH/STH control | engaging key WASH parters in all districts of Kagera, Shinyanga, Kigoma,Mara, Mwanza: | conference package, allowances, stationaries, transport,
SP1: Social mobilisation and Awareness creation
Production of Integrated IEC/BCC Materials
Re printing IEC/BCC Materials | Developing, Printing, distribution of IEC/BCC materials, media, : /All Envision | consultatancy fee, conference package, allowances, quotations, funds, transport, | bar: 2017-10-01
Re printing IEC/BCC Materials | All SCI | consultatancy fee, conference package, allowances, quotations, funds, transport,
Re printing IEC/BCC Materials | All CNTD | consultatancy fee, conference package, allowances, quotations, funds, transport,
Develop and produce IEC/BCC material for High Risk Adults (HRA) for Schistosomiasis | all 185 councils with HRA targeted | consultatancy fee, conference package, allowances, quotations, funds, transport,
Dissemination of IEC/BCC materials | All districts under Envision, SCI and CNTD: link with other advocacy & mobilization activities eg.
Media Awareness campaign
Media awareness meetings | Kagera, Shinyanga, Kigoma,Mara, Mwanza: ALL ENVISION, DAR,
Community Sensitization
Community Sensitization in nomadic districts | Longido, Ngorongoro, Monduli, Kiteto, Simanjiro, e.t.c. | conference package, transport, allowances
Community Sensitization in nomadic districts
Disemininaiton Meetings for NTD Scale down plans: sustaining the gains, surveillance, next steps. | all districts scalling down districts: 100 districts for LF and or Trachoma | letters, conference package, transport, allowance
Development and Production of Cultural appropriate Radio and TV Spots
Develop and produce, Jingles, radio and TV adverts for MDA campaigns | All districts under Envision, SCI and CNTD | quotations; contracting | bar: 2017-08-01
Airing of jingles, Radio and Tv adverts in all identified media companies | All districts under Envision, SCI and CNTD | quotations; contracting | bar: 2017-09-01; 2017-12-01; 2018-03-01; 2018-06-01; 2018-09-01; 2018-12-01
Airing of radio and Tv programs of NTDs awareness quarterly | All districts under Envision, SCI and CNTD | quotations; contracting
Year Long NTD Knowledge Translation Campaign
BCC Campaign in nomadic and hard to reach communities for improving MDA uptake uptake of morbidity | identified hard to reach districts | quotations; contracting
SP1: Regional/District Coordination
MDA Supervision-1
SP2: Strategic planning
Finalization of National NTD Masterplan 2017-2021 | bar: 2017-08-01
Development of NTD Policy guidelines | bar: 2017-10-01
Cross border meeting on Trachoma | bar: 2017-07-17
Cross border meeting with Malawi and Mozambique | bar: 2017-10-01
Technical Working Group-STH&SHISTO | Meeting of subject experts to deliberate on key eliminaiton issues and advise the MoH | conference package, allowance, transport, | bar: 2017-12-01; 2018-05-01
Technical Working Group-Trachoma | Meeting of subject experts to deliberate on key eliminaiton issues and advise the MoH | conference package, allowance, transport, | bar: 2017-12-01; 2018-05-01
Technical Working Group-OCHO & LF | Meeting of subject experts to deliberate on key eliminaiton issues and advise the MoH | conference package, allowance, transport, | bar: 2017-12-01; 2018-05-01
Technical Working Group-TOEAC Meeting | Meeting of subject experts to deliberate on key eliminaiton issues and advise the MoH | conference package, allowance, transport, | bar: 2018-02-01
Quarterly review metings for TT, - DFID/TRUST |  | conference package, allowance, transport,
Annual Joint Planning Meeting | all stakehoders review and plan ahead | bar: 2018-05-01
Publications Writing Workshops | bar: 2017-11-01
National Review/Planning Meeting | National Program Coordinators meet to review achievements and forge ways ahead: all regions and all districts invited. Learn and stratergize: disseminate | conference package, allowance, transport,
Regional Review/Planning meetings | all districts with IVM+ALB and ZITH MDA, for Oct 2017, and August 2018 MDAs. | conference package, allowance, transport, | bar: 2017-10-01
Regional Review/Planning meetings | All districts with PZQ+/ALB under ENVISION support | conference package, allowance, transport, | bar: 2018-03-01
Regional Review/Planning meetings | Shinyanga, Kigoma, Kagera, Mara, Mwanza, Simiyu | conference package, allowance, transport, | bar: 2018-01-01 to 2018-02-01
Regional Review/Planning meetings | Dar es Salaam | conference package, allowance, transport, | bar: 2017-08-01
District Review/Planning meetings | all districts with IVM+ALB and ZITH MDA | conference package, allowance, transport,
District Review/Planning meetings | All districts with PZQ+/ALB under ENVISION support | conference package, allowance, transport,
District Review/Planning meetings | Shinyanga, Kigoma, Kagera, Mara, Mwanza | conference package, allowance, transport,
District Review/Planning meetings | Dar es Salaam | conference package, allowance, transport,
Support Advocacy and coordination of WASH forum | To conduct NTD/WASH inception and follow up Meeetings | conference package, allowance, transport, | bar: 2017-11-01
Laboratory Capacity support | to leverage in country skills for oncho and LF based on the strategic plans: to conduct meetings of lab experts and LF/ONCHO
Extension of BCC Strategy | revise and change as per new masterplan and program strategies
Update LF Dossier | data collection from districts and compilation into the dossier document | bar: 2017-10-01; 2018-04-01
Update Trachoma Dossier | data collection from districts and compilation into the dossier document | bar: 2017-10-01; 2018-04-01
SP3: MDA registration
MDA Registrartion (HH Census) | Only in district IVM+ALB, + ZITH | bar: 2017-10-01 to 2017-11-01; 2018-07-01 to 2018-08-01
SP3: MDA drug distribution
IVM+ALB Drug distribution | To conduct Mass Drug Administration in DSM Municipal Councils | bar: 2017-08-01
All other IVM+ALB ENVISION districts | bar: 2017-10-01 to 2017-11-01; 2018-08-01
PZQ+/ALB Drug distribution | Shinyanga, Kigoma, Kagera, Mara, Mwanza | bar: 2018-02-01 to 2018-03-01
Dar es Salaam | bar: 2018-02-01
ENVISION supported districts with NO IVM+ALB Package | bar: 2018-05-01 to 2018-06-01
ENVISION supported districts with IVM+ALB Package | bar: 2018-02-01 to 2018-03-01
ZITH Drug distribution | MDA in 9 districts: Bahi, Chemba, Kongwa, Ngara, Liwale, Kiteto, Simanjiro, Chunya & Songwe | bar: 2017-10-01 to 2017-11-01
MDA in Agust 2018 Planned for Zithromax: 7 districts of: Longido, Monduli, Ngorongoro, Bahi, Chemba, Kiteto, Simanjiro | bar: 2018-08-01
SP4: Monitoring and Evalulation
Sentinel and Spot Check Sites Assessments for LF, STH and Schisto
SSA for LF: pre TAS1 | 15 districts in Lindi, Tanga, Pwani and Mtwara regions | bar: 2018-04-01
SSA for STH/SCH: in lake zone | 21 districts in Mwanza, Kagera, Shinyanga, Mara and Kigoma
TAS1-STH in 19 districts;
Re TAS 1 in 3 districts | Chemba, Kondoa DC, Kondoa TC
TAS 1 in 16 districts | Dar, Tanga and Lindi
F-TAS 2 (include OV 16 RDT) | 58 districts in Mbeya, Iringa, Njombe, Ruvuma,
Trachoma Surveys
TIS | 9 Districts:
TSS | 7 Districts:
TT Only Survey | HKI Funding (where TF is Low)
Oncho Surveys
Oncho Epidemiological Surveys: | Tunduru Focus
Oncho Monitoring | Ruvuma
Entomology | Tunduru, Ruvuma
Oncho elimination mapping
POST MDA Coverage survey
Lake zone: PZQ+ALB | Kagera, Mwanza, Shinyanga, Mara Kigoma
Dar IVM+ALB | Dar es salaam: CNTD
NTD electronic Database
NTD Database: selected districts
data entry into national database | continous - in house
NTD /MDA Perfomance & Review meeting
National Quartely NTD/ MDA Perfomance Review meeting | National NTD Secretariate (Ministry & IMA Team) 3 days training
Regional NTD/ MDA Perfomance Review meeting | After MDA Data collection -Emphasis in low performing councils (18 Zithromax & 28 Oncho)
Reporting to MOH/WHO/Partners
WHO- JR
ITI-TEMF
EPRIF,
capacity building on data management
WHO pc data banck, Forms, e.t.c
SP4: Drug logistics
Drugs Stock Verification | Verification of medicines stocks: IMA 20 IUs, CNTD-6 Ius and SCI 39 councils
Drugs application
WHO JRSPC
ITI-TEMF
ENVISION
Drugs Clearance | Clearing of PRZ, IVM and ZITH
MDA Drugs and supplies transportation: Adhoc | Transportation of MDA Drug and supplies to 20 IMA regions and 5 SCI
Drug transportation | Transportation where medicines arrived late and / MSD delays
Drugs reverse logistics | Collections of medicines left from HF to the Districts
SP4: Morbidity control and Surgery
Hydrocoele Camps: |  |  | 2017-12-01: 2016-05-09
Statoil Support: Mtwara region | Mtwara, Camp for up to 100 patients
CNTD Support: | Dar es Salaam
End Fund | Tabora, Dar and 350 patients
IMA support
other partners
Lymphoedema Management Activities:
Lymphoedema Management in costal belt
morbidity mapping
TT Surgeries:
DFIF/TRUST | Arusha, Manyara, Dodoma, Pwani, Mtwara, Lindi
IANET | Ruvuma,Korogwe, Handeni, Kilindi, Kisarawe
KCCO/EndFund | Ngorongoro
SP4: Capacity Building/Training
TOT(Training of Trainers)
Training of Trainers-Central | Training of National Team
TOT: Training of Trainers Regions | See abovein planning meeting
Training of Trainers-Regional+Districts | 58 councils in all IVM+ALB & Zith DISTRICTS (except Monduli, Ngorongoro, Longido)
Training of Trainers | Dar es Salaam
Training of Trainers | Ngorongoro, Monduli, Longido
TOT(Training of Trainers)School MDA
TOT(Training of Trainers)School MDA | all ENVISION
TOT(Training of Trainers)School MDA | SCI
TOT(Training of Trainers)School MDA | DSM
Training of FLHWs
Training of FLHWs for MDA | AS ABOVE
Training of FLHWs for MDA | AS ABOVE
Training of FLHWs for MDA | AS ABOVE
Training of FLHWs for MDA(Zithromax) | AS ABOVE
Training of CDDs
Training of CDDs for MDA | AS ABOVE
Training of CDDs for MDA | AS ABOVE
Training of CDDs for MDA(Zithromax) | AS ABOVE
Training of Teachers
Training of teachers for SMDA | AS ABOVE
Training of teachers for SMDA | AS ABOVE
Training of teachers for SMDA | AS ABOVE
Training of teachers for SMDA | AS ABOVE
Training of teachers for SMDA | AS ABOVE
Other Training
Finance training for accountants in new Districts/Regions | selected envision districgts
SP4: Supportive Supervision | update as per above activity plans
National ToT - SS Capacity Building | bar: 2017-10-01 to 2017-11-01
SS Advocacy and Community Mobilisation
IVM & ALB MDA + Zithromax | bar: 2017-10-01 to 2017-11-01
Zithromax MDA | bar: 2018-05-01 to 2018-11-01
Zithromax MDA | bar: 2018-05-01 to 2018-11-01
School MDA | bar: 2017-11-01 to 2018-02-01
School MDA | bar: 2018-06-01 to 2018-12-01
SS MDA Training
Community MDA (IVM +ALB + Zithromax) | bar: 2017-10-01 to 2017-11-01
Zithromax MDA | bar: 2018-06-01 to 2018-11-01
Zithromax MDA | bar: 2018-05-01 to 2018-06-01
School MDA | bar: 2018-01-01 to 2018-02-01
School MDA | bar: 2018-12-01
SS Drug Distribution -- MDA
IVM + ALB + Zithromax MDA | bar: 2017-11-01
Zithromax MDA | bar: 2018-07-01 to 2018-11-01
Zithromax MDA | bar: 2018-06-01
School MDA | bar: 2018-02-01
School MDA | bar: 2018-12-01
SS MDA Data Collection and Reporting
Community MDA (IVM +ALB + Zithromax) | bar: 2017-11-01
Zithromax MDA | bar: 2018-07-01 to 2018-11-01
Zithromax MDA | bar: 2018-06-01
School MDA | bar: 2018-02-01
School MDA | bar: 2018-12-01
SS on Morbidity Management
SS on TT Surgery
SS on Hydrocelectomy
SS on Lymphodema management
Note on O84: Moses Stephen: link with AJPM, DO IT JU
Note on B114: Moses Stephen: NEEDS more discussion with proposal developers and review