## INTRO
Annual Work Plan
As part of the global efforts to accelerate expansion of preventive chemotherapy (PC) for elimination and control of lymphatic filariasis, schistosomiasis, soil-transmitted helminthiases and onchocerciasis, the World Health Organization (WHO) facilitates the supply of necessary medicines. In order to request for medicines, submission of the Annual Work Plan together with the Joint Request for selected PC medicines and the Joint Reporting Form is a requisite.
Annual Work Plan allows the national programmes to identify the specific objectives to be achieved in the year, to focus on the key activities that needs to be implemented to achieve the said objectives, and to identify the gap in financial and technical resources to achieve the objectives. It also allows WHO to closely monitor the progress of the national programmes, and to identify the obstacles and coordinate for provision of financial and technical support in time.
Information to be included in the Annual Work Plan
Name of country
Implementation year
Relevant preventive chemotherapy diseases
Specific programmatic targets to achieve in the year
Annual work plan matrix comprising a list of activities and sub-activities with:
- Timeline of implementation
- Estimated cost
- Available or committed funds
- Funding gap
- Funders
Format of the Annual Work Plan
i) | There is no prescribed format; the annual work plan can be excel or word file as long as the required information is contained. Example is given in the following worksheet.
ii) | Annual work plan matrix can be automatically generated using the Tool for Integrated Planning and Costing (TIPAC).

## ANNUAL_WORKPLAN
ANNUAL WORK PLAN
1. Name of country | The Gambia
2. Implementation year | Jan | 2018 | to | Dec | 2018
| month | year |  | month | year
3. Relevant PC diseases
4. Specific goals to be achieved in the year | i) To achieve 100% national coverage for STH in Banjul and Kombo South Districts
ii) To conduct one epidemiological survey for all for SCH and STH
iii) To institute Monitoring and Evaluation implement for SCH and STH
5. Annual work plan matrix | [12 empty] | 69000
Activities and sub-activities | Timeline for implementation | [11 empty] | Estimated cost | Available funding | Funding gap | Funders
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | USD | USD | USD
Annual planning and review | [12 empty] | 4000 | 0 | 4000 | WHO Funding Support | bar: Timeline for implementation Feb to Timeline for implementation Jul
Annual planning meeting | [12 empty] | 2500 | 0 | 2500 | WHO Funding Support | bar: Timeline for implementation Jun
National stakeholders meeting | [12 empty] | 1000 | 0 | 1000 | WHO Funding Support | bar: Timeline for implementation Jul
Conduct MDA Planning Meeting | [12 empty] | 500 | 0 |  | WHO Funding Support | bar: Timeline for implementation Feb to Timeline for implementation Mar
Training | [12 empty] | 5000 | 0 | 5000 | WHO Funding Support | bar: Timeline for implementation Mar to Timeline for implementation Apr; Timeline for implementation Sep to Timeline for implementation Oct
Training of drug distributors | [12 empty] | 5000 | 0 | 5000 | WHO Funding Support | bar: Timeline for implementation Mar to Timeline for implementation Apr; Timeline for implementation Sep to Timeline for implementation Oct
MDA logistics | [12 empty] | 7000 | 0 |  | WHO Funding Support | bar: Timeline for implementation Jan to Timeline for implementation Mar; Timeline for implementation Jul to Timeline for implementation Aug
Request funds for MDA Logistics | [12 empty] | 0 | bar: Timeline for implementation Jan; Timeline for implementation Sep to Timeline for implementation Oct
Procure MDA Logistics( Fuel, statineries, Banners, Posters, etc) | [12 empty] | 7000 | 0 |  | WHO Funding Support | bar: Timeline for implementation Mar to Timeline for implementation Apr; Timeline for implementation Sep to Timeline for implementation Oct
Social mobilization | [12 empty] | 6500 | 0 | 6500 | WHO Funding Support | bar: Timeline for implementation Jan to Timeline for implementation Jun
Conduct Launching of MDA | [12 empty] | 2000 | 0 |  | WHO Funding Support | bar: Timeline for implementation Apr
Sensitize school and Local Authorities | [12 empty] | 1000 | 0 |  | WHO Funding Support | bar: Timeline for implementation Feb to Timeline for implementation Apr
Sensitize schools and Communities | [12 empty] | 2000 | 0 |  | WHO Funding Support | bar: Timeline for implementation Mar to Timeline for implementation Apr
Conduct TV and Radio Panel Discussion | [12 empty] | 1500 | 0 |  | WHO Funding Support
Drug logistics | [12 empty] | 0 |  | 0 | bar: Timeline for implementation Jan to Timeline for implementation Jun; Timeline for implementation Oct to Timeline for implementation Nov
Drug request | [12 empty] | 0 |  | 0
Drug repackaging | [12 empty] | 0 |  | 0
Drug transportation to districts | [12 empty] | 0 |  | 0 | bar: Timeline for implementation Apr; Timeline for implementation Oct
Drug distribution | [12 empty] | 15000 | 0 | 15000 | WHO Funding Support | bar: Timeline for implementation Apr to Timeline for implementation Jun; Timeline for implementation Oct to Timeline for implementation Dec
MDA1 (IVM + ALB) | [12 empty] | 0 |  | 0
MDA2 (DEC + ALB) | [12 empty] | 0 |  | 0
MDA3 (IVM) | [12 empty] | 0 |  | 0
T1 (ALB/MBD + PZQ) | [12 empty] | 0 |  | 0
T2 (PZQ) | [12 empty] | 0 |  | 0
T3 (ALB/MBD) (DSA for teams Supervisors and Drivers) | [12 empty] | 15000 | 0 | 15000 | WHO Funding Support | bar: Timeline for implementation Apr to Timeline for implementation Jun; Timeline for implementation Nov
Monitoring and evaluation | [12 empty] | 31500 | 0 | 31500 | WHO Funding Support
Develop Costed monitoring and evaluation plan and Adapt tools | [12 empty] | 5000 | 0 |  | WHO Funding Support | bar: Timeline for implementation Jan to Timeline for implementation Mar
Conduct Quarterly Monitoring&Supervision | [12 empty] | 1500 | 0 |  | WHO Funding Support | bar: Timeline for implementation Jul to Timeline for implementation Dec
LF sentinel/spot check sites survey | [12 empty] | 0 | 0 | 0 | WHO Funding Support
SCH and/or STH prevalence survey | [12 empty] | 25000 | 0 | 25000 | WHO Funding Support | bar: Timeline for implementation Jul to Timeline for implementation Dec
ONC epidemiological survey | [12 empty] | 0 | 0 | 0
LF TAS | [12 empty] | 0 | 0 | 0
Evaluation Unit 1 | [12 empty] | 0 | 0 | 0
Evaluation Unit 2 | [12 empty] | 0 | 0 | 0
6. Attachment
LF
STH
SCH
ONCHO
Joint Request for Selected PC Medicines
Joint Reporting Form
Joint Request for Selected PC Medicines
Joint Reporting Form
LF
STH
SCH
ONCHO

## Example
ANNUAL WORK PLAN
1. Name of country | The Gambia
2. Implementation year |  |  | to
| month | year |  | month | year
3. Relevant PC diseases
4. Specific goals to be achieved in the year
5. Annual work plan matrix | [5 empty] | 0
Activities and sub-activities | Timeline for implementation |  |  |  |  | Estimated cost | Available funding | Funding gap | Funders
[6 empty] | USD | USD | USD
6. Attachment
Joint Request for Selected PC Medicines
Joint Reporting Form
LF
STH
SCH
ONCHO